## Slide 1
CPEG-AI周报
2026年05月15日
报告人：Edward Zhang

## Slide 2
Team | Content | Answer | 
AI Team | The server has encountered an issue and needs to be addressed | 3/4/2026- 6/4/2026 | The vendor inspects the status of the server
 |  | 7/4/2026 | The vendor has confirmed that one GPU in the server is faulty
 |  | 8/4/2026 - TBD | Vendor confirmed 3 servers are normal; 1 shows signs of damage. A detailed evaluation report will be sent to the buyer by email.
Meeting topic reply

## Slide 3
FII-CNSBG-CPEG-AI团队 Project List 2026
1
Technical Direction | Type | No. | Prio. | Projects | Scene function description | Client | Product Line address | OT | AT | Due date Completed project | Due date Completed SOW | Due date launch Esign | Due date close Esign | Project status | Esign status | Ver | Prj PO-FC Value (USD) | Acceptance criteria | Note
Intelligent Software | Computer Vision | 1 | P1 | AI quality inspection product packing for | Use computer vision to check if the product packaging process is being followed correctly | Amazon | B08-3F | CBD-AE 黄公寿 | AI 阮明黃 | 2026/2/7 | The user has confirmed close project, so no further writing is needed | 2026/4/02 | 2026/5/02 | Closed | On going | v2.1 | $10,000 | Based on Esign | Calculate the value and reconfirm the product information of the project
 |  | 2 | TBD | IP CAM AI Project [Fuction A: Smart Inspection for safety phase 2] | Full-Site Safety Monitor with Self-Detection (2/3/4F B08) | Apollo & Rhea | B08 2/3/4F | Security 文实 | AI 平越豪 | TBD | 2026/3/16 | 2026/4/03 | 2026/5/03 | Open (Under Review) | On-going | TBD | $30,000 | Based on Esign | Sent emails to remind the user to sign the eSign document
 |  | 3 | TBD | IP CAM AI Project[Fuction B: Intelligent monitoring IPCAM for safety] | Full-Site Safety Monitor with Self-Detection (2/3/4F B08) | Apollo & Rhea | B08 2/3/4F | Security 文实 | AI 平越豪 | 2026/6/30 | 2026/3/18 | 2026/4/03 | 2026/5/03 | On-going | On-going | TBD | $60,000 | Based on Esign | Sent emails to remind the user to sign the eSign document

## Slide 4
FII-CNSBG-CPEG-AI团队 Project List 2026
1
Technical Direction | Type | No. | Prio. | Projects | Scene function description | Client | Product Line address | OT | AT | Due date Completed project | Due date Completed SOW | Due date launch Esign | Due date close Esign | Project status | Esign status | Ver | Prj PO-FC Value (USD) | Acceptance criteria | Note
Intelligent Software | Computer Vision | 4 | P1 | IP CAM AI Project [Fuction C: Auto BBS phase 3] | Full-Site Safety Monitor with Self-Detection (2/3/4F B08) | Apollo & Rhea | B08 1/2/3/4F | Security 文实 | AI 平越豪 | 2026/3/31 | 2026/3/20 | 2026/4/05 | 2026/5/05 | On-going | On-going | v1.4 | $16,000 | Based on Esign | Sent emails to remind the user to sign the eSign document
 |  | 5 | P1 | Check PCB Xray_F12 | Verify PCB X-ray images for completeness and auto-archive them. | Nic | JBD F12 Xray | JBD 阮玉德 | AI 丁仲皇维 | 2026/6/10 | 2026/3/14 | 2026/4/07 | 2026/6/20 | On-going | On-going | v0.1 | $10,000 | Based on Esign | (1) The Esign project initiation form has been completed (2) Developing project

## Slide 5
FII-CNSBG-CPEG-AI团队 Project List 2026
1
Technical Direction | Type | No. | Prio. | Projects | Scene function description | Client | Product Line address | OT | AT | Due date Completed project | Due date Completed SOW | Due date launch Esign | Due date close Esign | Project status | Esign status | Ver | Prj PO-FC Value (USD) | Acceptance criteria | Note
Intelligent Software | Computer Vision | 6 | TBD | Project A - AI quality inspection Kronos product in Test station | Use computer vision to check if the weighing time on the product meets the standard | Kronos | Fulian B08-2F | CBD-ME Duncan | AI 阮明黃 | TBD | 2026/3/17 | 2026/4/8 | 2026/5/08 | Open | Open | TBD | $18,000 | Based on Esign | Sent emails and messages on Wechat to remind the user to sign the Esign document
 |  | 7 | TBD | Project B - AI quality inspection Kronos product in Packing station | Use computer vision to check if workers are packing products according to the correct procedure | Kronos | Fulian B08-2F | CBD-ME Duncan | AI 阮文龙 | TBD | 2026/3/18 | 2026/4/10 | 2026/5/10 | Open | Open | TBD | $18,000 | Based on Esign | Sent emails and messages on Wechat to remind the user to sign the Esign document
 |  | 8 | TBD | DOE-Reflow oven | Predict the temperature for the welding machine | N/A | on system of Software department (Fulian B09-4F) | ME YunTao | AI 范英秀 | 2026/01/20 | 2026/3/10 | 2026/4/04 | 2026/5/04 | Closed | On going | v1.0 | $10,000 | Based on Esign | (1) Sent emails to remind the user to sign the Esign document (2) Sent response email to the user

## Slide 6
FII-CNSBG-CPEG-AI团队 Project List 2026
1
Technical Direction | Type | No. | Prio. | Projects | Scene function description | Client | Product Line Address | OT | AT | Due date Completed project | Due date Completed SOW | Due date launch Esign | Due date close Esign | Project status | Esign status | Ver | Prj PO-FC Value (USD) | Acceptance criteria | Note
 |  | 9 | TBD | AI Smart Translation | Translation language options: Chinese, Vietnamese, and English. | N/A | on system of Software department (Fulian B09-4F) | Fulian B08 QA | AI 范英秀 | 2026/01/24 | 2026/03/11 | 2026/4/06 | 2026/5/30 | Closed | On going | v1.0 | $10,000 | Based on Esign | (1) The program needs to be installed on the server. (2) Data is currently being transferred to the server.
 |  | 10 | P1 | Lighthouse 服務器降本 | Install 5 usecase website for lighthouse on DT server | Fulian CBD | Fulian B08 | CBD-DT 黃趙五 | AI 陳文俊 | 2026/6/30 | Already approved by the AI​&DT managers | 2026/4/10 | 2026/7/10 | On going | On going | v2.2 | $32,000 | Based on Esign | Use Case 1,3,5: All functionalities operate normally Use Case 4: The LLM, Onmiverse is not available. Onmiverse was updated to take data from new port 49100 --> new application has summited to request access new port Use Case 2: Onmiverser is still not working due to lack of chiller IP --> new application has summited to request access new IP
Multi-AI | Maintain software | 11 | TBD | Maintain all AI software | Maintain all AI software developed in 2025 | All Customer | All Product Line | All Users | AI 阮明黃 | TBD | TBD | TBD | TBD | Open | Open | TBD | $50,000 | Based on Esign | The quotation details have been sent

## Slide 7
OT： DT 黃趙五; AT: AI 潘洛興
Phase 1: Install usecase 1,2,3,5 on DT's Server_10.72.75.14 (2x GPU-PRO6000)
2
Project | Use case | IP/Port | Functionality | Status | Responsible | Describe Current Status
LightHouse | 1 | 10.72.75.16:443 | Login | Done | 文宝, Panda, AnyScript | 
 |  |  | LLM | Done |  | 
 |  |  | Web UI Interaction | Done |  | 
 | 3 | 10.72.75.16:8081 | Login | Done |  | 
 |  |  | LLM | Done |  | 
 |  |  | Web UI Interaction | Done |  | 
 | 2 | 10.72.75.14:8081 | Login | Done | 徐逸兴, Panda, AnyScript, 陳冠瑋(Kuan-Wei Chen) Peter | Onmiverse data has been moved to the new server (72.75.14)
 |  |  | Onmiverse | On-going |  | 
 |  |  | Web UI Interaction | Done |  | 
 | 4 | 10.72.75.18:443 | Login | Done | 徐逸兴, Panda, 陳冠瑋(Kuan-Wei Chen) Peter | 1. Real-time data is only available on the main UI, sub-UI do not display this data. 2. The LLM currently is not working.(This feature link with Case 5) 3. Onmiverse data was transferred to the new server (72.75.14) and then to 72.75.41. The Onmiverse function is not yet operational.
 |  |  | Real-time data | Done |  | 
 |  |  | LLM | On-going |  | 
 |  |  | Onmiverse | On-going |  | 
 |  |  | Web UI Interaction | Done |  | 
 | 5 | 10.72.75.31:8081 | Login | Done | 安之君, Panda, AnyScript | The requested application for LLM has been approved, we will continue to fix it.
 |  |  | Real-time data | Done |  | 
 |  |  | LLM | On-going |  | 
 |  |  | Web UI Interaction | Done |  | 
I. Overview

## Slide 8
Case | Function | Progress (Green: Done/Closed; Yellow: Ongoing; Other color: Open) | Due date
2 | Onmiverse | 1. Create access application to transfer data – Done-阮功俊英, 潘落興-26/04/08 2. Setting server and create new VM (75.42) to store data of case 2 OMV – Done-Panda-26/04/07 3. Transfer data from old server (93.48) to new server (75.14) and then to VM42 (75.42)–Done-TARG 陳冠瑋(Kuan-Wei Chen) Peter-26/04/13 | 26/04/15
 |  | 4. Get chiller MQTT data source address–On going- 陳冠瑋(Kuan-Wei Chen) Peter, 阮功俊英 (1) OMV Use case 2 receives data from more than 4 different IP addresses; we are compiling them into a list before submitting it. The application has been submitted and is awaiting approval.– Due Date: D days (D is the actual number of days it takes for the application to be approved.) | D+5
 |  | 5. Re-configure and deploy OMV web- TARG 陳冠瑋(Kuan-Wei Chen) Peter, 阮功俊英 | D+8
 |  | 6. Run OMV Kit app service & web service (change port to 8080)- TARG 陳冠瑋(Kuan-Wei Chen) Peter, 阮功俊英 | D+8
 |  | 7. Update i-frame on main website- AnyScript | D+11
 |  | 8. Test website function- TARG 陳冠瑋(Kuan-Wei Chen) Peter, 阮功俊英 | D+16
4 | Onmiverse | 1. Create access application to transfer data – Done-阮功俊英, 潘落興-26/04/08 2. Setting server & create new VM (75.41) to store data of case 4 OMV– Done-Panda-26/04/07 3. Transfer data from old server (93.48) to new server (75.14) and then to VM42 (75.42)–Done-TARG陳冠瑋(Kuan-Wei Chen) Peter-26/04/13 | 26/04/15
 |  | 4. Test website function – On going-鄧潘英, TARG Peter, TARG Panda (1) (1) Omniverse service retrieves data from server 72.75.41 via ports 8080 and 49100. Currently, only port 8080 is accessible  Waiting for the access application to open port 49100- Due Date: D days | D+5
 | LLM | Submit internet application for IOC access with updated port- On-going- 阮功俊英, 潘落興  The application has been submitted and is awaiting approval. | D
 |  | 2. Deploy ioc service- Ongoing- TARG袁小利 | D+7
 |  | 3. Test LLM function - 鄧潘英 | D+12
5 | LLM | Submit internet application for IOC access with updated port- On-going- 阮功俊英, 潘落興  The application has been submitted and is awaiting approval. | D
 |  | 2. Deploy ioc service - Ongoing- TARG袁小利 | D+7
 |  | 3. Test LLM function -阮功俊英 | D+12
OT： DT 黃趙五; AT: AI 潘洛興
Phase 1: Install usecase 1,2,3,5 on DT's Server_10.72.75.14 (2x GPU-PRO6000)

## Slide 9
OT： DT 黃趙五; AT: AI 潘洛興
Fig 1. Acess Application Form
Phase 1: Install usecase 1,2,3,5 on DT's Server_10.72.75.14 (2x GPU-PRO6000)