## Slide 1
CPEG-AI周报
2026年05月15日
报告人：Edward Zhang

## Slide 2
Team | Content | Answer | 
AI Team | The server has encountered an issue and needs to be addressed | 3/4/2026- 6/4/2026 | The vendor inspects the status of the server
 |  | 7/4/2026 | The vendor has confirmed that one GPU in the server is faulty
 |  | 8/4/2026 - TBD | Vendor confirmed 3 servers are normal; 1 shows signs of damage. A detailed evaluation report will be sent to the buyer by email.
Meeting topic reply

## Slide 3
FII-CNSBG-CPEG-AI团队 Project List 2026
1
Technical Direction | Type | No. | Prio. | Projects | Scene function description | Client | Product Line address | OT | AT | Due date Completed project | Due date Completed SOW | Due date launch Esign | Due date close Esign | Project status | Esign status | Ver | Prj PO-FC Value (USD) | Acceptance criteria | Note
Intelligent Software | Computer Vision | 1 | P1 | AI quality inspection product packing for | Use computer vision to check the packaging process | Amazon | B08-3F | CBD-AE 黄公寿 | AI 阮明黃 | 2026/2/7 | User confirmed to close project. | 2026/4/02 | 2026/5/31 | Closed | On going | v2.1 | $10,000 | Based on Esign | Calculate the value and reconfirm the product information of the project
 |  | 2 | TBD | IP CAM AI Project [Fuction A: Smart Inspection for safety phase 2] | Full-Site Safety Monitor with Self-Detection (2/3/4F B08) | Apollo & Rhea | B08 2/3/4F | Security 文实 | AI 平越豪 | TBD | 2026/3/16 | 2026/4/03 | 2026/6/5 | Open | On-going | TBD | $30,000 | Based on Esign | Sent emails to remind the user to sign the eSign document
 |  | 3 | TBD | IP CAM AI Project[Fuction B: Intelligent monitoring IPCAM for safety] | Full-Site Safety Monitor with Self-Detection (2/3/4F B08) | Apollo & Rhea | B08 2/3/4F | Security 文实 | AI 平越豪 | 2026/6/30 | 2026/3/18 | 2026/4/03 | 2026/7/10 | On-going | On-going | TBD | $60,000 | Based on Esign | Sent emails to remind the user to sign the eSign document

## Slide 4
FII-CNSBG-CPEG-AI团队 Project List 2026
1
Technical Direction | Type | No. | Prio. | Projects | Scene function description | Client | Product Line address | OT | AT | Due date Completed project | Due date Completed SOW | Due date launch Esign | Due date close Esign | Project status | Esign status | Ver | Prj PO-FC Value (USD) | Acceptance criteria | Note
Intelligent Software | Computer Vision | 4 | P1 | IP CAM AI Project [Fuction C: Auto BBS phase 3] | Full-Site Safety Monitor with Self-Detection (2/3/4F B08) | Apollo & Rhea | B08 1/2/3/4F | Security 文实 | AI 平越豪 | 2026/3/31 | 2026/3/20 | 2026/4/05 | 2026/6/15 | On-going | On-going | v1.4 | $16,000 | Based on Esign | Sent emails to remind the user to sign the eSign document
 |  | 5 | P1 | Check PCB Xray_F12 | Verify PCB X-ray images for completeness and auto-archive them. | Nic | JBD F12 Xray | JBD 阮玉德 | AI 丁仲皇维 | 2026/6/10 | 2026/3/14 | 2026/4/07 | 2026/6/20 | On-going | On-going | v0.1 | $10,000 | Based on Esign | (1) Coding is finished, wait the user the get the IP for final setup

## Slide 5
FII-CNSBG-CPEG-AI团队 Project List 2026
1
Technical Direction | Type | No. | Prio. | Projects | Scene function description | Client | Product Line address | OT | AT | Due date Completed project | Due date Completed SOW | Due date launch Esign | Due date close Esign | Project status | Esign status | Ver | Prj PO-FC Value (USD) | Acceptance criteria | Note
Intelligent Software | Computer Vision | 6 | TBD | Project A - AI quality inspection Kronos product in Test station | Use computer vision to check if the weighing time on the product meets the standard | Kronos | Fulian B08-2F | CBD-ME Duncan | AI 阮明黃 | TBD | 2026/3/17 | 2026/4/8 | 2026/6/12 | Open | Open | TBD | $18,000 | Based on Esign | Sent emails and messages on Wechat to remind the user to sign the Esign document
 |  | 7 | TBD | Project B - AI quality inspection Kronos product in Packing station | Use computer vision to check if workers are packing products according to the correct procedure | Kronos | Fulian B08-2F | CBD-ME Duncan | AI 阮文龙 | TBD | 2026/3/18 | 2026/4/10 | 2026/6/17 | Open | Open | TBD | $18,000 | Based on Esign | Sent emails and messages on Wechat to remind the user to sign the Esign document
 |  | 8 | TBD | DOE-Reflow oven | Predict the temperature for the welding machine | N/A | on system of Software department (Fulian B09-4F) | ME YunTao | AI 范英秀 | 2026/01/20 | 2026/3/10 | 2026/4/04 | 2026/7/31 | Closed | On going | v1.0 | $10,000 | Based on Esign | (1) Sent emails to remind the user to sign the Esign document (2) Sent response email to the user

## Slide 6
FII-CNSBG-CPEG-AI团队 Project List 2026
1
Technical Direction | Type | No. | Prio. | Projects | Scene function description | Client | Product Line Address | OT | AT | Due date Completed project | Due date Completed SOW | Due date launch Esign | Due date close Esign | Project status | Esign status | Ver | Prj PO-FC Value (USD) | Acceptance criteria | Note
 |  | 9 | TBD | AI Smart Translation | Translation language options: Chinese, Vietnamese, and English. | N/A | on system of Software department (Fulian B09-4F) | Fulian B08 QA | AI 范英秀 | 2026/01/24 | 2026/03/11 | 2026/4/06 | 2026/5/30 | Closed | On going | v1.0 | $10,000 | Based on Esign | Data is currently being transferred to the server.
 |  | 10 | P1 | Lighthouse 服務器降本 | Install 5 usecase website for lighthouse on DT server | Fulian CBD | Fulian B08 | CBD-DT 黃趙五 | AI 陳文俊 | 2026/6/30 | Already approved by the AI​&DT managers | 2026/4/10 | 2026/7/10 | On going | On going | v2.2 | $32,000 | Based on Esign | Use Case 1,3,5: All functionalities operate normally Use Case 4: The LLM, Onmiverse is not available. Use Case 2: Onmiverser is not working
Multi-AI | Maintain software | 11 | TBD | Maintain all AI software | Maintain all AI software developed in 2025 | All Customer | All Product Line | All Users | AI 阮明黃 | TBD | TBD | TBD | TBD | Open | Open | TBD | $50,000 | Based on Esign | The quotation details have been sent

## Slide 7
OT： DT 黃趙五; AT: AI 潘洛興
Phase 1: Install usecase 1,2,3,5 on DT's Server_10.72.75.14 (2x GPU-PRO6000)
2
Project | Use case | IP/Port | Functionality | Status | Responsible | Describe Current Status
LightHouse | 1 | 10.72.75.16:443 | Login | Done | 文宝, Panda, AnyScript | 
 |  |  | LLM | Done |  | 
 |  |  | Web UI Interaction | Done |  | 
 | 3 | 10.72.75.16:8081 | Login | Done |  | 
 |  |  | LLM | Done |  | 
 |  |  | Web UI Interaction | Done |  | 
 | 2 | 10.72.75.14:8081 | Login | Done | 徐逸兴, Panda, AnyScript, 陳冠瑋(Kuan-Wei Chen) Peter | Onmiverse is not working due to data inaccessible
 |  |  | Onmiverse | On-going |  | 
 |  |  | Web UI Interaction | Done |  | 
 | 4 | 10.72.75.18:443 | Login | Done | 徐逸兴, Panda, 陳冠瑋(Kuan-Wei Chen) Peter | The LLM currently is not working.(This feature link with Case 5)
 |  |  | Real-time data | Done |  | 
 |  |  | LLM | On-going |  | 
 |  |  | Onmiverse | Done |  | 
 |  |  | Web UI Interaction | Done |  | 
 | 5 | 10.72.75.31:8081 | Login | Done | 安之君, Panda, AnyScript | 
 |  |  | Real-time data | Done |  | 
 |  |  | LLM | Done |  | 
 |  |  | Web UI Interaction | Done |  | 
I. Overview

## Slide 8
Case | Function | Progress (Green: Done/Closed; Yellow: Ongoing; Other color: Open) | Due date
2 | Onmiverse | 1. Create access application to transfer data – Done-阮功俊英, 潘落興-26/04/08 2. Setting server and create new VM (75.42) to store data of case 2 OMV – Done-Panda-26/04/07 3. Transfer data from old server (93.48) to new server (75.14) and then to VM42 (75.42)–Done-TARG 陳冠瑋(Kuan-Wei Chen) Peter-26/04/13 | 26/04/15
 |  | 4. Get chiller MQTT data source address–On going- 陳冠瑋(Kuan-Wei Chen) Peter, 阮功俊英 (1) OMV Use case 2 receives data from more than 4 different IP addresses; we are compiling them into a list before submitting it. The application has been submitted and is awaiting approval.– Due Date: D days (D is the actual number of days it takes for the application to be approved.) | D+5
 |  | 5. Re-configure and deploy OMV web- TARG 陳冠瑋(Kuan-Wei Chen) Peter, 阮功俊英 | D+8
 |  | 6. Run OMV Kit app service & web service (change port to 8080)- TARG 陳冠瑋(Kuan-Wei Chen) Peter, 阮功俊英 | D+8
 |  | 7. Update i-frame on main website- AnyScript | D+11
 |  | 8. Test website function- TARG 陳冠瑋(Kuan-Wei Chen) Peter, 阮功俊英 | D+16
4 | Onmiverse | 1. Create access application to transfer data – Done-阮功俊英, 潘落興-26/04/08 2. Setting server & create new VM (75.41) to store data of case 4 OMV– Done-Panda-26/04/07 3. Transfer data from old server (93.48) to new server (75.14) and then to VM42 (75.42)–Done-TARG陳冠瑋(Kuan-Wei Chen) Peter-26/04/13 | 26/04/15
 |  | 4. Test website function – On going-鄧潘英, TARG Peter, TARG Panda (1) (1) Omniverse service retrieves data from server 72.75.41 via ports 8080 and 49100. Currently, only port 8080 is accessible  Waiting for the access application to open port 49100- Due Date: D days | D+5
 | LLM | Submit internet application for IOC access with updated port- On-going- 阮功俊英, 潘落興  The application has been submitted and is awaiting approval. | D
 |  | 2. Deploy ioc service- Ongoing- TARG袁小利 | D+7
 |  | 3. Test LLM function - 鄧潘英 | D+12
5 | LLM | Submit internet application for IOC access with updated port- On-going- 阮功俊英, 潘落興  The application has been submitted and is awaiting approval. | D
 |  | 2. Deploy ioc service - Ongoing- TARG袁小利 | D+7
 |  | 3. Test LLM function -阮功俊英 | D+12
OT： DT 黃趙五; AT: AI 潘洛興
Phase 1: Install usecase 1,2,3,5 on DT's Server_10.72.75.14 (2x GPU-PRO6000)

## Slide 9
OT： DT 黃趙五; AT: AI 潘洛興
Fig 1. Acess Application Form
Phase 1: Install usecase 1,2,3,5 on DT's Server_10.72.75.14 (2x GPU-PRO6000)