## Slide 1
OT： DT 黃趙五; AT: AI 潘洛興
Phase 1: Install usecase 1,2,3,5 on DT's Server_10.72.75.14 (2x GPU-PRO6000)
2
Project | Use case | IP/Port | Functionality | Status | Responsible | Describe Current Status
LightHouse | 1 | 10.72.75.16:443 | Login | Done | 文宝, Panda, AnyScript | 
 |  |  | LLM | Done |  | 
 |  |  | Web UI Interaction | Done |  | 
 | 3 | 10.72.75.16:8081 | Login | Done |  | 
 |  |  | LLM | Done |  | 
 |  |  | Web UI Interaction | Done |  | 
 | 2 | 10.72.75.14:8081 | Login | Done | 徐逸兴, Panda, AnyScript, 陳冠瑋(Kuan-Wei Chen) Peter | Onmiverse data has been moved to the new server (72.75.14)
 |  |  | Onmiverse | On-going |  | 
 |  |  | Web UI Interaction | Done |  | 
 | 4 | 10.72.75.18:443 | Login | Done | 徐逸兴, Panda, 陳冠瑋(Kuan-Wei Chen) Peter | 1. Real-time data is only available on the main UI, sub-UI do not display this data. 2. The LLM currently is not working.(This feature link with Case 5) 3. Onmiverse data was transferred to the new server (72.75.14) and then to 72.75.41. The Onmiverse function is not yet operational.
 |  |  | Real-time data | Done |  | 
 |  |  | LLM | On-going |  | 
 |  |  | Onmiverse | On-going |  | 
 |  |  | Web UI Interaction | Done |  | 
 | 5 | 10.72.75.31:8081 | Login | Done | 安之君, Panda, AnyScript | 
 |  |  | Real-time data | Done |  | 
 |  |  | LLM | Done |  | 
 |  |  | Web UI Interaction | Done |  | 
I. Overview

## Slide 2
Case | Function | Progress (Green: Done/Closed; Yellow: Ongoing; Other color: Open) | Due date
2 | Omniverse | 1. Create access application to transfer data – Done-阮功俊英, 潘落興-26/04/08 2. Setting server and create new VM (75.42) to store data of case 2 OMV – Done-Panda-26/04/07 3. Transfer data from old server (93.48) to new server (75.14) and then to VM42 (75.42)–Done-TARG 陳冠瑋(Kuan-Wei Chen) Peter-26/04/13 | 26/04/15
 |  | 4. Get chiller MQTT data source address–On going- 陳冠瑋(Kuan-Wei Chen) Peter, 阮功俊英 (1) OMV Use case 2 receives data from more than 4 different IP addresses; we are compiling them into a list before submitting it. The application has been submitted and is awaiting approval.– Due Date: D days (D is the actual number of days it takes for the application to be approved.) (2) The application was rejected on 26/04/28 due to port 80 being considered high risk. This impacts OMV deployment, as all related OMV ports are included in the same application. New application was recreated with port separate from those associated with IOC and will be submit on 26/05/07 | D+5
 |  | 5. Re-configure and deploy OMV web- TARG 陳冠瑋(Kuan-Wei Chen) Peter, 阮功俊英 | D+8
 |  | 6. Run OMV Kit app service & web service (change port to 8080)- TARG 陳冠瑋(Kuan-Wei Chen) Peter, 阮功俊英 | D+8
 |  | 7. Update i-frame on main website- AnyScript | D+11
 |  | 8. Test website function- TARG 陳冠瑋(Kuan-Wei Chen) Peter, 阮功俊英 | D+16
4 | Omniverse | 1. Create access application to transfer data – Done-阮功俊英, 潘落興-26/04/08 2. Setting server & create new VM (75.41) to store data of case 4 OMV– Done-Panda-26/04/07 3. Transfer data from old server (93.48) to new server (75.14) and then to VM42 (75.42)–Done-TARG陳冠瑋(Kuan-Wei Chen) Peter-26/04/13 | 26/04/15
 |  | 4. Test website function – On going-鄧潘英, TARG Peter, TARG Panda, Iverson(博丞) (1) Omniverse functionality is not yet running; currently finding and editing the config file (file nginx.conf, .sh file) for proper setup. | D+5
 | LLM | Submit internet application for IOC access with updated port- On-going- 阮功俊英, 潘落興  The application has been submitted and was rejected on 26/04/28 due to port 80 (IOC-related) being considered high risk | D
 |  | 2. Deploy ioc service- Ongoing- TARG袁小利 | D+7
 |  | 3. Test LLM function – Ongoing-鄧潘英  The LLM is still not available | D+12
5 | LLM | Submit internet application for IOC access with updated port- On-going- 阮功俊英, 潘落興  The application has been submitted and was rejected on 26/04/28 due to port 80 (IOC-related) being considered high risk | D
 |  | 2. Deploy ioc service - Ongoing- TARG袁小利 | D+7
 |  | 3. Test LLM function – Ongoing-阮功俊英  Currently, the LLM can response | D+12
OT： DT 黃趙五; AT: AI 潘洛興
Phase 1: Install usecase 1,2,3,5 on DT's Server_10.72.75.14 (2x GPU-PRO6000)