## Slide 1
OT： DT 黃趙五; AT: AI 潘洛興
Table 1: Phase 1-Install use case 1,2,3,5 on DT's Server_10.72.75.14 (2x GPU-PRO6000)
2
Project | Use case | IP/Port | Functionality | Status | Responsible | Describe Current Status
LightHouse Phase 1 | 1 | 10.72.75.16:443 | Login | Done | 文宝, Panda, AnyScript | 
 |  |  | LLM | Done |  | 
 |  |  | Web UI Interaction | Done |  | 
 | 3 | 10.72.75.16:8081 | Login | Done |  | 
 | 3 | 10.72.75.16:8081 | Login | Done |  | 
 |  |  | LLM | Done |  | 
 |  |  | Web UI Interaction | Done |  | 
 | 2 | 10.72.75.14:8081 | Login | Done | 徐逸兴, Panda, AnyScript, 陳冠瑋(Kuan-Wei Chen) Peter | A network access request has been submitted to allow connectivity from IP 159.138.228.193 to the server IP 10.72.75.14.
 |  |  | Web UI Interaction | Done |  | 
 |  |  | Onmiverse | On-going |  | 
 | 4 | 10.72.75.18:443 | Login | Done | 徐逸兴, Panda, 陳冠瑋(Kuan-Wei Chen) Peter | 1. LLM currently is not working.(This feature link with Case 5) 2. Onmiverse can display 3D scene of old server.
 |  |  | Real-time data | Done |  | 
 |  |  | LLM | On-going |  | 
 |  |  | Onmiverse | Done |  | 
 |  |  | Web UI Interaction | Done |  | 
 | 5 | 10.72.75.31:8081 | Login | Done | 安之君, Panda, AnyScript | 
 |  |  | Real-time data | Done |  | 
 |  |  | LLM | Done |  | 
 |  |  | Web UI Interaction | Done |  | 
I. Overview
Project | Use case | IP/Port | Functionality | Status | Responsible | Describe Current Status
LightHouse Phase 2 | 2 | 10.72.75.14:8081 | Onmiverse | On-going | 徐逸兴, Panda, AnyScript, 陳冠瑋(Kuan-Wei Chen) Peter | A network access request has been submitted to allow connectivity from IP 159.138.228.193 to the server IP 10.72.75.14.
 | 4 | 10.72.75.18:443 | Onmiverse | On-going | 徐逸兴, Panda, 陳冠瑋(Kuan-Wei Chen) Peter | Already moving data to new server.
Lighthouse Installation
Table 2: Phase 2-Install new Omniverse program of use case 2&4 to Server 10.72.92.47 (2x GPU-PRO6000)

## Slide 2
Case | Function | Progress (Green: Done/Closed; Yellow: Ongoing; Other color: Open) | Due date
2 | Omniverse | 1. Create access application to transfer data – Done-阮功俊英, 潘落興-26/04/08 2. Setting server and create new VM (75.42) to store data of case 2 OMV – Done-Panda-26/04/07 3. Transfer data from old server (93.48) to new server (75.14) and then to VM42 (75.42)–Done-TARG 陳冠瑋(Kuan-Wei Chen) Peter-26/04/13 | 26/04/15
 |  | 4. Get chiller MQTT data source address–On going- 陳冠瑋(Kuan-Wei Chen) Peter, 阮功俊英,潘落興 (1) The old application was rejected on 26/04/28 due to port 80 being considered high risk. This impacts OMV deployment, as all related OMV ports are included in the same application  New application was recreated with port separate from those associated with IOC and submitted on 26/05/07– Due Date: D days (D is the actual number of days it takes for the application to be approved.) | D+5
 |  | 5. Re-configure and deploy OMV web- TARG 陳冠瑋(Kuan-Wei Chen) Peter, 阮功俊英 | D+8
 |  | 6. Run OMV Kit app service & web service- TARG 陳冠瑋(Kuan-Wei Chen) Peter, 阮功俊英 | D+8
 |  | 7. Update i-frame on main website- AnyScript | D+11
 |  | 8. Test website function- TARG 陳冠瑋(Kuan-Wei Chen) Peter, 阮功俊英 | D+16
4 | Omniverse | 1. Create access application to transfer data – Done-阮功俊英, 潘落興-26/04/08 2. Setting server & create new VM (75.41) to store data of case 4 OMV– Done-Panda-26/04/07 3. Transfer data from old server (93.48) to new server (75.14) and then to VM42 (75.42)–Done-TARG陳冠瑋(Kuan-Wei Chen) Peter-26/04/13 | 26/04/15
 |  | 4. Test website function – On going-鄧潘英, TARG Peter, TARG Panda, Iverson(博丞) (1) We have re-tested using tmux, restarting the Kit app, and reconnecting through the URL, but the Omniverse connection issue still persists. | D+5
 | LLM | 1. Submit internet application for IOC access with updated port- On-going- 阮功俊英, 潘落興 (1) The application has been submitted and was rejected on 26/04/28 due to port 80 (IOC-related) being considered high risk  Woking with the security team to conduct an information security assessment and reconfirm the request before resubmission. | D
 |  | 2. Deploy ioc service- Ongoing- TARG袁小利 | D+7
 |  | 3. Test LLM function – Ongoing-鄧潘英 (1) The LLM is still not available, on 26/05/08, we tried to update the LLM API address and tested but the interface at that address is unavailable  Need to use the interface of IOC (2) The server is currently shutdown after reboot on 26/05/08, reason for rebooting is that one GPU is unavailable.  cannot test kit service. | D+12
5 | LLM | Submit internet application for IOC access with updated port- On-going- 阮功俊英, 潘落興 | D
 |  | 2. Deploy ioc service - Ongoing- TARG袁小利 | D+7
 |  | 3. Test LLM function – Done-阮功俊英  The LLM can response. | D+12 26/05/04
OT： DT 黃趙五; AT: AI 潘洛興
Lighthouse Installation